TextileBot

Project Plan & Team Assignments

WhatsApp ERP Assistant for Textile Businesses

March 2026

# The Team

| Person | Strength | Role | Key Responsibilities |
| --- | --- | --- | --- |
| Diyanesh | Make.com, Domain Knowledge, Client Network | Product Owner + No-Code Builder | Client relationships, sales, Make.com automations, Google Sheets admin setup, product decisions |
| Raghul | Multi-language Developer | Backend Developer | Tally connector, API logic, bot engine (Python/FastAPI), database design, WhatsApp API integration |
| Megha | DevOps, Docker, Cloud Infra | Infrastructure Lead | Server setup, Docker containers, deployment pipeline, monitoring, SSL, domain config, backups |
| Shiv (Australia) | Automation Enthusiast | QA + Automation + Support | Make.com flow building, testing all scenarios, writing user guides, first-line client support (timezone advantage for overnight monitoring) |

# Tech Stack

Combining no-code tools with custom code for the best of both worlds.

| Component | Tool / Tech | Built By | Type |
| --- | --- | --- | --- |
| WhatsApp Integration | Gupshup / Twilio API | Diyanesh + Raghul | API + Make.com |
| Message Router | Make.com Scenarios | Diyanesh + Shiv | No-Code |
| AI Message Parser | Claude API / OpenAI | Diyanesh | API Call via Make.com |
| Tally Connector | Python + Tally XML API | Raghul | Custom Code |
| Database | PostgreSQL | Raghul + Megha | Managed Service |
| Photo Storage | Google Drive / S3 | Diyanesh | No-Code (Make.com) |
| Admin Dashboard | Google Sheets + AppSheet / Retool | Diyanesh + Shiv | No-Code / Low-Code |
| Infrastructure | Docker + Cloud (AWS/DO) | Megha | DevOps |

# V1 Build Timeline (8 Weeks)

Raghul works part-time (evenings + weekends). Everyone else contributes around their schedules.

## Weeks 1-2: Foundation

| Owner | Task | Deliverable |
| --- | --- | --- |
| Diyanesh | Set up Gupshup/Twilio account, get WhatsApp Business API approved, create Make.com scenarios for receiving/sending WhatsApp messages | Bot receives and replies to messages |
| Raghul | Set up Python/FastAPI project, design database schema (clients, users, tally_data, photos), create REST API endpoints | API server running locally |
| Megha | Provision cloud server, set up Docker environment, configure PostgreSQL, set up domain + SSL for API | Server live and accessible |
| Shiv | Document all Make.com scenarios, test WhatsApp message flow end-to-end, create test cases spreadsheet | Test plan ready |

## Weeks 3-4: Core Intelligence

| Owner | Task | Deliverable |
| --- | --- | --- |
| Diyanesh | Build Make.com scenario: WhatsApp message > Claude API > parse intent > route to correct data query. Test Tamil + English messages. | Bot understands natural language |
| Raghul | Build Tally connector: Python script that reads Tally XML API (stock, invoices, POs, outstanding), syncs to PostgreSQL. Test with sample Tally data. | Tally data in cloud DB |
| Megha | Deploy API server to cloud, set up Docker Compose for all services, configure automated backups for database | Production environment ready |
| Shiv | Test 50+ message variations in Tamil and English, document which ones fail, help refine the Claude API prompt | NLP accuracy report |

## Weeks 5-6: Integration + Admin

| Owner | Task | Deliverable |
| --- | --- | --- |
| Diyanesh | Build admin layer using Google Sheets + AppSheet/Retool: client management, user registration, photo gallery, usage logs. | Admin dashboard live |
| Raghul | Connect all pieces: Make.com > API > Database > Tally data. Build user auth (phone number verification). Multi-tenant data isolation. | Full pipeline working |
| Megha | Set up monitoring and alerts, configure log rotation, performance testing, ensure auto-restart on failures | Production-grade infra |
| Shiv | End-to-end testing: register a business > add users > send queries > receive data > store photos. Test edge cases. | QA sign-off |

## Weeks 7-8: Polish + First Client

| Owner | Task | Deliverable |
| --- | --- | --- |
| Diyanesh | Onboard first pilot client (free trial). Install Tally connector at their location. Gather feedback daily. Refine bot responses. | First live client! |
| Raghul | Bug fixes from real usage, performance optimization, error handling improvements, graceful failure messages | Stable product |
| Megha | Production monitoring during pilot, set up alerts for downtime, ensure backups are working, scale resources if needed | Zero-downtime operations |
| Shiv | Write user onboarding guide, create FAQ document, set up feedback collection process, monitor overnight (AU timezone) | Documentation complete |

# Monthly Running Costs

Estimated costs once live with first 5-10 clients.

| Service | Monthly Cost | Notes |
| --- | --- | --- |
| WhatsApp Business API (Gupshup) | Rs. 1,000 - 2,000 | Pay per conversation, ~Rs. 0.50-1 each |
| Cloud Server | Rs. 1,000 - 1,500 | DigitalOcean or AWS small instance |
| AI API (Claude/OpenAI) | Rs. 500 - 1,500 | For natural language parsing, usage-based |
| Make.com | Rs. 750 - 1,500 | Pro plan for WhatsApp scenarios |
| Cloud Storage (Photos) | Rs. 200 - 500 | Google Drive or S3 |
| Domain + SSL | Rs. 100 | Annual cost divided monthly |
| TOTAL | Rs. 3,500 - 7,000 | Before revenue. Scales with clients. |

# Admin Dashboard Options

Since we are going no-code/low-code, here are the options for the admin panel where Diyanesh manages clients, users, and photos:

Option 1 - Google Sheets + AppSheet (Recommended): Use Google Sheets as the database and Google AppSheet to create a mobile-friendly admin app on top of it. Free for up to 10 users. Quick to set up, easy to modify.

Option 2 - Retool: More powerful admin dashboard builder. Connects directly to PostgreSQL. Free tier available. Better for complex views but has a learning curve.

Option 3 - NocoDB / Baserow: Open-source Airtable alternatives. Self-hosted on our server (Megha can set this up). Full control, no per-user costs. Looks professional.

# Immediate Action Items

What each person should do this week to kick off the project.

Diyanesh: Complete client conversations (ask about Tally setup). Set up Gupshup account. Register Meta Business Account. Get dedicated SIM card for WhatsApp bot number. Share this document with the team.

Raghul: Set up Python development environment. Research Tally Prime XML API documentation. Create a GitHub/GitLab repository for the project. Build a basic FastAPI server.

Megha: Choose cloud provider (recommend DigitalOcean for simplicity). Create account. Provision a small server. Set up Docker on it. Share SSH access with Raghul.

Shiv: Create a shared Google Sheet for tracking tasks and bugs. Sign up for Make.com if not already. Watch 2-3 YouTube tutorials on WhatsApp Business API + Make.com integration. Start documenting the project wiki.

TextileBot  |  Built for the textile industry